## Project Team
Name | Role
Developer FE-A | Front-End Developer
Developer FE-B | Front-End Developer
Developer FE-C | Front-End Developer
Developer BE-A | Back-End Developer
Developer BE-B | Back-End Developer
Tester 1 | QA Tester
Tester 2 | QA Tester
Tester 3 | QA Tester

## Project Task Assignment
Front-End / Back-End | Requirement | Developer | Dev Time (Days) | QA | Test Time (Days)
Front-End | 1 | Developer FE-A | 0.5 | Tester 3 | 0.5
Front-End | 2 | Developer FE-A | 0.5 | Tester 3 | 0.5
Front-End | 3 | Developer FE-A | 1 | Tester 3 | 0.5
Front-End | 4 | Developer FE-B | 0.5 | Tester 2 | 0.5
Front-End | 5 | Developer FE-B | 2 | Tester 1 | 1
Front-End | 6 | Developer FE-B | 2 | Tester 1 | 1
Front-End | 7 | Developer FE-B | 1 | Tester 1 | 1.5
Front-End | 8 | Developer FE-C | 2 | Tester 2 | 2
Front-End | 9 | Developer FE-C | 2 | Tester 2 | 2
Back-End | 1 | Developer BE-A | 4 | Tester 1 | 3
Back-End | 2 | Developer BE-B | 3 | Tester 3 | 1
Back-End | 3 | Developer BE-B | 1 | Tester 3 | 1
Back-End | 4 | Developer BE-A | 2 | Tester 2 | 1

## Kanban Board
To Do | In Development | In Testing | Done
Requirement 1 - Front-End
Requirement 2 - Front-End
Requirement 3 - Front-End
Requirement 4 - Front-End
Requirement 5 - Front-End
Requirement 6 - Front-End
Requirement 7 - Front-End
Requirement 8 - Front-End
Requirement 9 - Front-End
Requirement 1- Back-End
Requirement 2 - Back-End
Requirement 3 - Back-End
Requirement 4 - Back-End